# Technical Proposal: NOC and Data Centre Managed Services for Metro Rail Corporation (2023)

Client: Pragati Metro Rail Corporation (fictional) | Year: 2023 | Result: LOST | Synthetic past proposal for the TenderBridge demo

| Metadata | Value |
| --- | --- |
| Document ID | KB-PP-003 |
| Client (fictional) | Pragati Metro Rail Corporation (fictional) |
| Year | 2023 |
| Result | lost |
| Topic tags | NOC, data centre, managed services, transport |
| Approved for reuse | Partial: sections 3 and 4 only; sections 1, 5 and 6 contain outdated or unsupported statements and are NOT approved for reuse |

# 1. Executive summary (NOT approved for reuse)

Nimbus guarantees 99.99% uptime across all systems and has managed three State Data Centres.

Our ISO/IEC 27001:2013 certified ISMS covers all Nimbus locations.

# 2. Understanding of scope

The client operates a 30-rack data centre and an operations control centre network across 28 stations.

# 3. NOC operating model (approved for reuse)

24x7 NOC with tiered L1/L2/L3 support; alerts auto-ticketed; daily network health report by 10:00; monthly trend analysis of recurring incidents.

Shift handover checklist with open P1/P2 incidents

ISP escalation matrix with timelines

Quarterly preventive maintenance calendar

# 4. Change and configuration management (approved for reuse)

CMDB built from auto-discovery within 90 days; weekly change advisory board; emergency change process with retrospective approval within 24 hours.

# 5. Team (NOT approved for reuse)

Proposed security lead: CISM-certified security lead with 13 years of experience (name withheld).

# 6. Commercial assumptions (NOT approved for reuse)

Penalties capped at 5% of monthly charges; payment within 30 days.

# NOC tooling

The NMS polls devices every 60 seconds and receives traps; alerts are correlated to suppress duplicates and create tickets automatically. Topology maps are kept current from discovery.

# ISP and field coordination

Each link has an ISP escalation matrix with timelines. Field engineers are dispatched through the ITSM tool with GPS-stamped visit records.

# Network and security devices tower

The network tower manages core and access switches, routers, firewalls, load balancers and security appliances inside the data centre. All changes to firewall rules go through the change process with a business justification and an expiry date for temporary rules.

Configuration backups of all devices are taken daily and compared with the previous version; unexpected differences raise an alert. Firmware is kept within the OEM's supported versions.

Monthly: firewall rule review, unused rule clean-up

Quarterly: configuration compliance audit

Half-yearly: network architecture review with the client

# Governance structure

A three-tier governance model: (1) a steering committee chaired by the client and attended by the Nimbus VP - Public Sector Business, meeting quarterly; (2) a monthly service review chaired by the client's nodal officer with the Nimbus project manager; (3) daily operations calls between shift in-charges and client IT staff.

Escalation matrix with names and response times for each level

Minutes and action logs maintained in the ITSM tool

Quarterly service improvement plan

# Service level commitments

Nimbus commits to the service levels in the client's RFP. Nimbus does not offer service levels beyond the RFP unless they are priced and evidenced.

| Parameter | Commitment |
| --- | --- |
| Infrastructure availability | As per RFP SLA |
| P1 response / resolution | As per RFP SLA |
| Monthly SLA report | By the 7th of the following month |
| Root cause analysis for P1 | Within 5 working days |

# Risk register (top risks and mitigations)

| Risk | Mitigation | Owner |
| --- | --- | --- |
| Incomplete knowledge transfer from incumbent | Structured KT plan, shadowing, CMDB rebuild from discovery | Project Manager |
| Key personnel attrition | Named back-ups, retention bonus, 30-day overlap for replacements | Delivery Head |
| OEM support delays | Back-to-back support agreements, escalation contacts at OEMs | DC Operations Lead |
| Security incident | 24x7 monitoring, CERT-In reporting in 6 hours, incident playbooks | Security Lead |
| Scope creep | Change control through CAB and contract change notes | Project Manager |

# Quality assurance

Engagement quality plan within 30 days of Go-Live; internal quality audits twice a year; customer satisfaction survey every quarter; corrective actions for every SLA breach.

# Exit management

Exit plan within 90 days of Go-Live, updated yearly; six months of exit support with knowledge transfer, documentation, configurations and credentials handed over.

# Assumptions

Client provides workspace, access, and timely approvals for changes.

Facility management (power, cooling) is provided by the client's facility agency.

Prices and staffing as of 2023; to be revalidated for any reuse.

# Debrief and lessons learned (internal)

Result: lost on technical score (68.5 of 100; qualifying score 70). The client's debrief cited: weak transition plan, no evidence for the 99.99% uptime claim, and a security lead certification that could not be verified.

Lessons: never state uptime guarantees beyond the tender's SLA; cite only completed projects with completion certificates; check personal certification validity before proposing key personnel.